## Sheet1
BLACK TIE & TAILS GALA
| RESPONSIBLE PARTY | DEADLINE | NOTES
AUCTION
PROCUREMENT OF LIVE AUCTION ITEMS
PROCUREMENT OF SILENT AUCTION ITEMS
LISTINGS FOR PROGRAM (LIVE AUCTION)
DONOR LIST FOR PROGRAM
PRODUCTION OF BID SHEETS
DEVELOP LOGISTICS FOR CHECKOUT
VOLUNTEER TRAINING FOR CHECKOUT
SET-UP COMPUTER NETWORK ON-SITE--TEST
REVIEW CHECK-OUT PROCEDURES
DISPLAY/SHOWCASE AUCTION ITEMS
THANK YOU NOTES TO AUCTION ITEM DONORS
INVITATIONS / TABLE SALES/ REGISTRATION | Person Responsible
SAVE THE DATE EMAIL TO LAST YEARS ATTENDEE LIST
ADDRESS/MAIL PRINTED INVITATIONS
SOLICIT SENIOR STAFF SUPPORT
SOLICIT NAMES/EMAIL ADDRESSES FOR ALL CONFIRMED ATTENDEES
FINALIZE MEAL CHOICES FOR ALL CONFIRMED ATTENDEES
SEND THANK-YOU EMAIL TO ATTENDEES
LOGISTICS | Person Responsible
CONFIRM LOCATION
CONFIRM LAYOUT/UTILIZATION OF SPACE
CONFIRM SOUND/LIGHTING VENDOR
CONFIRM MENU
FAVORS FOR GUESTS
CENTERPIECES (toys and treats)
SET-UP FOR DOGGIE SPA
FOOD FOR VOLUNTEERS (snacks vs. a meal)
AV
PROGRAM | Person Responsible
CONFIRM JOHN BECKER AS EMCEE
CONFIRM JAMES CATES AS AUCTIONEER
FINALIZE MINUTE-BY-MINUTE RUNDOWN
CONFIRM ENTERTAINMENT FOR COCKTAIL HOUR
CONFIRM ENTERTAINMENT FOR EVENT
CONFIRM ANY SPEAKERS
CONFIRM PHOTOGRAPHER AND SET
TIES & TAILS SET UP, SALES, VOLUNTEERS
PRIZE FOR TIES & TAILS
PROMOTION | Person Responsible
PRESS RELEASE SCHEDULE
WRITE PRESS RELEASES AND DISTRIBUTE ON SCHEDULE
SUBMIT EVENT FOR COMMUNITY CALENDARS
BOOK GUEST SPOTS ON LOCAL NEWS PROGRAMS
DEVELOP AND EXECUTE A SOCIAL MEDIA PROMOTIONAL PLAN
FINALIZE PROGRAM CONTENT
SECURE SPONSOR LOGOS FOR PROGRAM/OTHER MATERIALS
DESIGN/PRINT EVENT PROGRAM
VOLUNTEERS | Person Responsible
Determine Volunteer needs
Recruit Volunteers (for specific jobs)
Draft Volunteer job descriptions
Provide advance communication/training for vols.
DOGGIE CARE | Person Responsible